## GanttChart
Task Name | Start Date | Duration (Days) | End Date | Status
Overall Project Duration | 2020-09-29 | 242 | 2021-05-29 | InProgress
Project Video Pitch Idea | 2020-10-14 | 2 | 2020-10-16 | Completed/Approved
Project Video Pitch Editing | 2020-10-16 | 2 | 2020-10-18 | Completed
Reflecting Journals
October Journal | 2020-09-29 | 32 | 2020-10-31 | Completed
November Journal | 2020-11-01 | 29 | 2020-11-30 | InProgress
December Journal | 2020-12-01 | 30 | 2020-12-31 | Pending
January Journal | 2021-01-01 | 30 | 2021-01-31 | Pending
February Journal | 2021-02-01 | 27 | 2021-02-28 | Pending
March Journal | 2021-03-01 | 30 | 2021-03-31 | Pending
April Journal | 2021-04-01 | 29 | 2021-04-30 | Pending
Project Proposel Document
Project Proposal | 2020-11-03 | 5 | 2020-11-08 | Completed
Documentation | 2020-11-03 | 3 | 2020-11-06 | Completed
GanttChart | 2020-11-07 | 1 | 2020-11-08 | Completed
Project Ethics Form | 2020-11-06 | 1 | 2020-11-07 | Completed
Mid Point Presentation
Implementation | 2020-11-09 | 43 | 2020-12-22 | Pending
Documentation | 2020-11-09 | 38 | 2020-12-17 | Pending
Video Presentation | 2020-12-17 | 5 | 2020-12-22 | Pending
Software Development
Implementation | 2020-12-23 | 137 | 2021-05-09 | Pending
Front End Dev. | 2020-12-23 | 40 | 2021-02-01 | Pending
Back End Dev. | 2021-02-01 | 59 | 2021-04-01 | Pending
Connecting Front & Back | 2021-04-01 | 29 | 2021-04-30 | Pending
Deploiment | 2021-04-30 | 9 | 2021-05-09 | Pending
Final Presentation
Implementation | 2021-05-01 | 8 | 2021-05-09 | Pending
Documentation | 2021-05-03 | 6 | 2021-05-09 | Pending
Video Presentation | 2021-05-09 | 7 | 2021-05-16 | Pending
Project Showcase | 2021-05-24 | 5 | 2021-05-29 | Pending